HARMONISED IMPLEMENTATION TOOLS FOR INTERREG PROGRAMMES – TN/CBC

Project Progress Report Monitoring Checklist – FINAL

The monitoring checklist focuses on the content and financial checks done by Programme’s Joint Secretariat. The main objectives of this document are: - to record the work of the programme and projects, - to have common standards, terminology, approach in the project monitoring, - to have transparent monitoring and input in case of complaints (if applicable), - to provide feedback for projects, - to record of what is not going well and keeping track of problems, - to ensure institutional memory.

Part A

A.1 Project progress report identification

| Project title | Pre-filled from project progress report |
| --- | --- |
| Project acronym | Pre-filled from project progress report |
| Project number | Pre-filled from project progress report |
| Project progress report number | Pre-filled from project progress report |
| Reporting period | DD.MM.YYYY – DD.MM.YYYY |
| Names of persons filling in the checklist |  |

A.2 Completeness of the report

| Administrative criteria | Description | Yes | No | NA | Comments |
| --- | --- | --- | --- | --- | --- |
| Delivered to the right location by the set deadline. | Day, time of the day or within a certain period. |  |  |  |  |
| Required number of project progress report versions is submitted. | Progress report is submitted in required number of paper and electronic versions. |  |  |  |  |
| Paper and electronic versions are identical. | The same templates are used for paper and for electronic version. The content is identical. |  |  |  |  |
| All obligatory annexes are submitted. | Obligatory annexes are attached where applicable. |  |  |  |  |
| The project progress report is signed by the authorised signatory. | The progress report and its annexes are signed where necessary. |  |  |  |  |
| Project progress report and its annexes are correctly filled in. | All applicable sections of the progress report are correctly filled in (no automatic errors or missing information). |  |  |  |  |

Part B – Project progress monitoring

| Nr | Monitoring questions | Yes | No | NA | Comments | Clarified |
| --- | --- | --- | --- | --- | --- | --- |
| B.1 | General information on project’s implementation |  |  |  |  |  |
| B.1.1 | Highlights of main achievement are cumulative (overview from start of the project to the current period), precise, interesting and understandable for non-specialists. |  |  |  |  |  |
| B.1.2 | The project website (if existing) is up to date. |  |  |  |  |  |
| B.1.3 | Information and publicity rules of the EU and the programme were complied with. |  |  |  |  |  |
| B.1.4 | In the case of the delayed project, the consequences are not significant for the achievement of project objectives. |  |  |  |  |  |
| B.2 | Detailed reporting per work package |  |  |  |  |  |
| B.2.1 | The progress on outputs, activities and their deliverables is clearly described and understandable. |  |  |  |  |  |
| B.2.2 | Outputs, activities and their deliverables are in line with application form and communication strategy (if available). If not, it is justified. |  |  |  |  |  |
| B.2.3 | There aren’t any obvious issues/shortcomings regarding the quality of delivered outputs and deliverables. |  |  |  |  |  |
| B.2.4 | The project is well on track to reach or surpass the target values in application form. |  |  |  |  |  |
| B.2.5 | Reported indicator values are realistic in view of the project progress. |  |  |  |  |  |
| B.2.6 | Investments (if applicable) are in line with the application form and properly progressing and documented. |  |  |  |  |  |
| B.2.7 | Target groups were involved in the development of main outputs delivered in this reporting period and are realistic. |  |  |  |  |  |
| B.2.8 | The description of problems is clear and complete and the adopted/proposed measures are suitable to overcome the problems. |  |  |  |  |  |

Part C - Project finance monitoring

| Nr | Monitoring questions | Yes | No | Comments | Clarified | Comments |
| --- | --- | --- | --- | --- | --- | --- |
| C.1 | The partnership agreement was signed by all partners reporting costs. |  |  |  |  |  |
| C.2 | The partnership agreement meets the programme minimum requirements. |  |  |  |  |  |
| C.3 | All relevant FLC certificates are available and valid. They are issued by designated controller(s). |  |  |  |  |  |
| C.4 | Amounts entered into the Project Progress Report are based on the available FLC certificates. |  |  |  |  |  |
| C.5 | The project is financially on track compared to the approved budget (including changes) and within the programme flexibility rules: - project total - per partner - per budget line - WP |  |  |  |  |  |
| C.6 | Deviations (if any) in the spending profile are acceptable and in line with the programme flexibility rules. |  |  |  |  |  |
| C.7 | Investments are financially on track compared to the approved budget (including changes). Deviations (if any) are justified. |  |  |  |  |  |
| C.8 | Forecast for the next report corresponds with the period target indicated in the application form (within the programme flexibility rules): - project total - per partner |  |  |  |  |  |
| C.9 | The project expenditure outside (the Union part of) the programme area is in line with the application form or it has been approved by the JS according to the programme procedures. |  |  |  |  |  |
| C.10 | The project expenditure corresponds with the activities carried out and is proportionate to the accomplished deliverables and outputs. - WP |  |  |  |  |  |

Part D - Assessment of project progress

D.1 What was the project’s main achievement or highlight in this reporting period? What can be used for programme promotion and capitalisation activities?

D.2 What is your conclusion regarding the progress of the project towards its objectives?

D.3 If applicable, actions (such as desk checks, on-the-spot-check, programme intervention, etc) to be taken based on monitoring of project’s reporting.

D.4 If applicable, programme’s remarks to be taken into account for the next project report.

Because of different programme requirements a description specifying what has to be checked needs to be added by each programme separately. There are some indications in Italics of what could be checked.

NA = Not applicable. Certain criteria might not be relevant for all projects within one call for proposals or programme.

If follow up is needed (in case of unfulfilled criterion), option NO should be ticked and the requirement could be described in the “comments” field.

NA = Not applicable

Text could be automatically transferred to the clarification letter sent to Lead partner.

When unclear issues are clarified, the person monitoring the project should record this.

Monitoring questions repeat for each work package.

Text could be automatically transferred to the clarification letter sent to Lead partner.

When unclear issues are clarified, the person monitoring the project should record this. Comment should be provided.